## Slide 1
IR3.1 Performance Testing
Executive Summary — XD CRM Program
Performance Testing Approach | Test Results | Account 360 Deep-Dive | Next Steps
CRM Program | XD Engineering
March 2026

## Slide 2
Agenda
01
Executive Summary — Key fixes delivered, results achieved & open items
02
Performance Testing Approach — Scope, methodology & load strategy
03
Test Volumes & Ramp Strategy — Load parameters, SLA thresholds & test setup
04
IR3.1 Performance Results — Initial vs. final run, scenario-level outcomes
05
Account 360 Deep-Dive — Response time breakdown & root cause
06
Next Steps & Action Plan — Active Salesforce engagement & Mar 11 resolution path

## Slide 3
Executive Summary — IR3.1 Performance Testing
Account 360 — In Progress
Objective: Validate IR3.1 CRM performance under production-scale load and bring all 360 pages within the 5s SLA threshold
RESOLVED — CRAID-2844
SAP Backend Optimization
SAP integration was causing excessive backend degradation across all 360 pages. Root-cause identified in redundant API calls and unoptimized query patterns. Post-fix, API response time stabilized to 3-4s avg.
RESOLVED — CRAID-3304
API Call Sequencing & Prioritization
API calls were executing in suboptimal sequence, causing compounding wait times. Work Orders calls reordered and prioritized. Result: ~2s reduction in page load. Premise & Customer 360 now fully within SLA.
Overall Outcomes
2 of 3 scenarios passing SLA
15-20s → 5.7s avg on Account 360
Premise & Customer 360 closed
IN PROGRESS — CRAID-3309
Salesforce Omni studio Framework Overhead
After SAP and API fixes, Account 360 still exceeds SLA due to foundational Omni studio component rendering overhead — independent of any code builds. Severity 1 case raised with Salesforce 03/07. Active architectural engagement ongoing.
Target resolution: March 11.
CRM Performance Testing | IR3.1

## Slide 4
Performance Testing Approach
Testing Scope
Salesforce UI
Mulesoft
SAP
What Are We Testing?
End-to-end XD CRM user workflows
Scenarios: Account 360, Premise 360, Customer 360 pages
Type: Performance (response time) + Load (concurrent users)
Focus: Salesforce CRM pages under realistic production load and extended stress testing
Test Volumes & Data
100 concurrent users × 25 calls each = 2,500 requests per hour
Each of the 2,500 records is unique (no data reuse)
2500 requests are across the value streams such as Account 360, Premise 360 and Customer 360
SLA Threshold: 90th percentile response time < 5 seconds
Ramp-Up Strategy
1 new user added every 3 seconds (gradual ramp)
100 UNIQUE users fully ramped after ~300 seconds (5 min)
Every 3 minutes a transaction is executed by the user
Duration: 3,600 seconds (1 hour) per test run
Tools & Infrastructure
Tool: Apache JMeter
Thread Groups configured per scenario
Monitoring: Avg response time + 90th percentile line
Industry standard: A good user experience falls close to > 5 sec
CRM Performance Testing | IR3.1

## Slide 5
IR3.1 Performance Test Results — Initial vs. Final Run Comparison
3
Scenarios Tested
Account · Premise · Customer 360
2 / 3
Initial Run Result
2 Resolved | 1 In Progress
CRAID-2844
Defect Filed
Raised against all 3 scenarios
2,500
Load Volume
100 users × 25 calls, all unique
Initial Run — Feb 20, 2026 (Reference)
Final Run — Mar 6, 2026
Scenario
Avg Resp
90 Percentile
Status
Avg Resp
90 Percentile
Status
SLA Met?
Account 360 — Login
0.680s
0.705s
Pass
0.578
0.713
Pass
Met
Account 360 — Homepage
0.588s
0.684s
Pass
0.584
0.746
Pass
Met
Account 360 — Search
0.243s
0.276s
Pass
0.240
0.305
Pass
Met
Account 360 Page
23.458s
32.478s
Failed
5.679
7.220
Failed
In Progress
Premise 360 — Login
0.680s
0.705s
Pass
0.749
0.750
Pass
Met
Premise 360 — Homepage
0.588s
0.684s
Pass
0.634
0.751
Pass
Met
Premise 360 — Search
0.255s
0.298s
Pass
0.246
0.315
Pass
Met
Premise 360 Page
22.880s
48.493s
Failed
1.983
2.332
Pass
Met
Customer 360 — Login
0.680s
0.705s
Pass
0.591
0.701
Pass
Met
Customer 360 — Homepage
0.588s
0.684s
Pass
0.571
0.712
Pass
Met
Customer 360 — Search
0.164s
0.196s
Pass
0.164
0.212
Pass
Met
Customer 360 Page
14.130s
27.719s
Failed
2.777
4.230
Pass
Met
Premise & Customer 360: Resolved ✅ | Account 360: Salesforce Omnistudio fix in progress (CRAID-3309, Sev1 raised 03/07)
CRM Performance Testing | IR3.1

## Slide 6
Account 360 — Response Time Breakdown
CRAID-3309 Active
End-to-End Page Load Timeline — Account 360 (Total: ~7-10 seconds | SLA Target: <5s)
API Layer: 3-4s — On Target
SF Omnistudio: 3-6s — In Fix
5s SLA
0s 2s 4s 6s 8s 10s
Mar 6 Run
API Layer — Performing Well
90% of API calls respond in <4s
SAP backend stabilized via CRAID-2844
API call sequence optimized via CRAID-3304
700 transactions executed across 100 users
Salesforce Omnistudio — Being Fixed
SF UI contributes 3-6s to page load time
Root cause: Omnistudio framework rendering overhead (component-level, not code-build related)
Severity 1 raised 03/07 — Salesforce architectural review underway
Current Result (Mar 6): Avg 5.679s | 90th pct 7.220s — API On Target | SF Omnistudio fix in progress, targeting <6.8s by Mar 11
CRM Performance Testing | IR3.1

## Slide 7
Status Update & Path to Resolution
CRAID-3309 | Account 360 Omnistudio | As of March 10, 2026
Salesforce Severity 1 raised 03/07 — Active correspondence underway. Salesforce engineering team engaged on Omnistudio architectural fix.
COMPLETED
Mar 7 — Sev1 Raised
Severity 1 case submitted to Salesforce. Omnistudio root cause fully documented and shared with SF engineering team.
IN PROGRESS
Mar 7-10 — Active Fix Dev
Ongoing correspondence with Salesforce. Architectural analysis and Omnistudio component optimization in progress. Fix being developed.
NEXT
Mar 11 — Fix & Validate
Deploy Omnistudio fix, run full performance re-test. Target: Account 360 under 6.8s, CRAID-3309 closed.
CRM Performance Testing | IR3.1