## Slide 1
IR3.1 Performance Testing
Executive Summary — XD CRM Program
01
Performance Testing Approach
02
Test Volumes & Ramp Strategy
03
IR3.1 Results — Initial & Latest Run
March 2026 | CRM Program

## Slide 2
Put an Agenda here

## Slide 3
High level summary as the first slide
Executive Summary: Account 360 Performance Remediation Status: 🔴 At Risk (Targeting March 11 Resolution) Objective: Reduce Account 360 page load time from current 8–10s to production baseline of ~6.8s. Current Performance Gap • Original State: 15–20 seconds (UAT 3.1 launch) • Current State: 8–10 seconds (Post-SAP & API optimization) • Target State: < 6.8 seconds Key Improvements to Date • SAP Optimization (CRAID 2844): Resolved backend degradation; API response times stabilized at 3–4s. • API Sequencing (CRAID 3304): Adjusted calling order (Work Orders priority). Successfully reduced load time by ~2s, though results were below expectations. Critical Blockers & Root Cause • Defect CRAID 3309: Current analysis points to Salesforce Omnistudio framework issues. The foundational components are causing inconsistent rendering speeds independent of recent code builds. • Action: Initiated a Severity 1 case with Salesforce for immediate architectural support. Timeline & Next Steps • Mar 7–10: Deep-dive diagnosis and collaboration with Salesforce Support to optimize Omnistudio component overhead. • Mar 11: Completion of fixes, performance re-test, and detailed status update. • ETA for Resolution: March 11, 2025Executive Summary: Account 360 Performance Remediation Status: 🔴 At Risk (Targeting March 11 Resolution) Objective: Reduce Account 360 page load time from current 8–10s to production baseline of ~6.8s. Current Performance Gap • Original State: 15–20 seconds (UAT 3.1 launch) • Current State: 8–10 seconds (Post-SAP & API optimization) • Target State: < 6.8 seconds Key Improvements to Date • SAP Optimization (CRAID 2844): Resolved backend degradation; API response times stabilized at 3–4s. • API Sequencing (CRAID 3304): Adjusted calling order (Work Orders priority). Successfully reduced load time by ~2s, though results were below expectations. Critical Blockers & Root Cause • Defect CRAID 3309: Current analysis points to Salesforce Omnistudio framework issues. The foundational components are causing inconsistent rendering speeds independent of recent code builds. • Action: Initiated a Severity 1 case with Salesforce for immediate architectural support. Timeline & Next Steps • Mar 7–10: Deep-dive diagnosis and collaboration with Salesforce Support to optimize Omnistudio component overhead. • Mar 11: Completion of fixes, performance re-test, and detailed status update. • ETA for Resolution: March 11, 2025

## Slide 4
Performance Testing Approach
Testing Scope
Salesforce UI
Mulesoft
SAP
Update this to bi-directional arrows to show end to end
What Are We Testing?
End-to-end XD CRM user workflows
Scenarios: Account 360, Premise 360, Customer 360 pages
Type: Performance (response time) + Load (concurrent users)
Focus: Salesforce CRM pages under realistic production load and extended stress testing
Test Volumes & Data
100 concurrent users × 25 calls each = 2,500 requests per hour
Each of the 2,500 records is unique (no data reuse)
2500 requests are across the value streams such as Account 360, Premise 360 and Customer 360
SLA Threshold: 90th percentile response time < 5 seconds
Ramp-Up Strategy
1 new user added every 3 seconds (gradual ramp)
100 UNIQUE users fully ramped after ~300 seconds (5 min)
Every 3 minutes a transaction is executed by the user
Duration: 3,600 seconds (1 hour) per test run
Tools & Infrastructure
Tool: Apache JMeter
Thread Groups configured per scenario
Monitoring: Avg response time + 90th percentile line
Industry standard: A good user experience falls close to > 5 sec
CRM Performance Testing | IR3.1

## Slide 5
IR3.1 Performance Test Results — Initial vs. Final Run Comparison
3
Scenarios Tested
Account · Premise · Customer 360
0 / 3
Initial Run Result
All 360 pages failed SLA (Feb 20)
CRAID-2844
Defect Filed
Raised against all 3 scenarios
2,500
Load Volume
100 users × 25 calls, all unique
Initial Run — Feb 20, 2026
Final Run — Mar 6, 2026
Scenario
Avg Resp
90 Percentile
Status
Avg Resp
90 Percentile
Status
SLA Met?
Account 360 — Login
0.680s
0.705s
Pass
0.578
0.713
Pass
Met
Account 360 — Homepage
0.588s
0.684s
Pass
0.584
0.746
Pass
Met
Account 360 — Search
0.243s
0.276s
Pass
0.240
0.305
Pass
Met
Account 360 Page
23.458s
32.478s
Failed
5.679
7.220
Failed
Not Met
Premise 360 — Login
0.680s
0.705s
Pass
0.749
0.750
Pass
Met
Premise 360 — Homepage
0.588s
0.684s
Pass
0.634
0.751
Pass
Met
Premise 360 — Search
0.255s
0.298s
Pass
0.246
0.315
Pass
Met
Premise 360 Page
22.880s
48.493s
Failed
1.983
2.332
Pass
Met
Customer 360 — Login
0.680s
0.705s
Pass
0.591
0.701
Pass
Met
Customer 360 — Homepage
0.588s
0.684s
Pass
0.571
0.712
Pass
Met
Customer 360 — Search
0.164s
0.196s
Pass
0.164
0.212
Pass
Met
Customer 360 Page
14.130s
27.719s
Failed
2.777
4.230
Pass
Met
Initial Run: All three 360 pages exceeded the 5s SLA — Defect CRAID-2844 filed. Final run results (Mar 6) to be updated above.
CRM Performance Testing | IR3.1

## Slide 6
Breakdown for Account 360 page
700 transactions were executed, API wise 90% responded in less than 4, Salesforce UI responded 4 to 6 seconds,
Across the board, the SF takes between 3 to 4 seconds, and API takes another 3 to 5 seconds.
Account
3309

## Slide 7
Next Steps / Actions
Defect CRAID 3309: Current analysis points to Salesforce Omnistudio framework issues. The foundational components are causing inconsistent rendering speeds independent of recent code builds.​ • Action: Initiated a Severity 1 case with Salesforce for immediate architectural support.​ Timeline & Next Steps​ • Mar 7–10: Deep-dive diagnosis and collaboration with Salesforce Support to optimize Omnistudio component overhead.​ • Mar 11: Completion of fixes, performance re-test, and detailed status update.​ • ETA for Resolution: March 11, 2025​
​