## Slide 1
DevOps Challenges
Root Cause Classification
This document presents a structured analysis of systemic delivery challenges observed across the XD program. Issues are classified by root cause — not symptoms.
Prepared for:
PwC Partners & Directors
Issue Classification
People
Behavior & Culture
Process
Execution Discipline
Structure
Org & Tooling
SOW
Planning & Scope
PwC | DevOps – Root Cause Classification | Confidential
Internal Use Only

## Slide 2
The Core Insight
DevOps is the aggregation point.
Not the root cause.
Every delivery pain point ultimately routes through DevOps — but the origins span four distinct domains:
People
Accountability, transparency,
client engagement culture
Process
Handoffs, PR classification,
collaboration overhead
Structure
No unified lead, constrained
environments, vendor dynamics
SOW
Release model not defined
in contract or planning
PwC | DevOps – Root Cause Classification | Confidential
Internal Use Only

## Slide 3
Code Issues (Dev)
↓
PR Delays / Rework
↓
Seen by FPL Dev Managers
↓
Escalated as “PR / DevOps issue”
↓
FPL Leadership hears: “DevOps problem”
↓
PwC Leadership hears same signal
↓
Pressure on DevOps
↓
Actual root cause (Dev quality / readiness) remains unresolved

## Slide 4
Current DevOps Process
CRM DevOps | IR3.1 Process Overview
01 Developer
Mostly Atomic Feature PR
Feature Branches →
XD Test R3
(in-sprint test env)
02 PwC DevOps
Combined PR + PD Steps
Combines PRs, reconciles
PD Steps → FPLSINT
Dev Team members forcing offshore DevOps to make manual tweaks
03 FPL DevOps
Package & Deploy
Batches(Builds packages) multi-project PRs
Deploys to Mainline SIT / UAT / Prod
Zero visibility for PwC

## Slide 5
Why 'DevOps' Becomes the Default Scapegoat
A structural misalignment — not a capability failure
HOW THE CLIENT SEES IT
"XD is one project."
FPL leadership thinks of the entire technology landscape as a unified product. In their view, when something goes wrong anywhere in delivery — whether it's a PR delay, a failed deployment, or a missed timeline — it becomes a DevOps issue.
The client has limited visibility into:
• Offshore vs onsite accountability splits
• Code readiness as a separate gate
• Vendor-driven friction (K-Force, TCS, etc.)
• Governance structural mismatches
HOW DELIVERY IS STRUCTURED
Multiple independent teams. 1 shared blame target.
In reality, delivery runs through multiple independent workstreams — each with different incentives, managers, and accountability models:
• PwC Dev (Offshore India) — code production
• PwC DevOps (Onsite) — release orchestration
• FPL Dev Managers — code review & approval
• FPL DevOps (Contractors) — env & infra
• Multiple external vendors — competing priorities
PwC | DevOps – Root Cause Classification | Confidential
Internal Use Only

## Slide 6
A · People Issues: Behavior, Accountability & Culture
Patterns observed across offshore team dynamics and client engagement
Ownership Gaps — Offshore Team
Reluctance to take end-to-end accountability without escalation
Strong contributors diluted by low-accountability team culture
Reactive posture: waits for direction rather than proactive resolution
Transparency & Communication
Known issues surfaced late — short-term effort saving causes larger downstream delays
Ambiguous status communication under pressure
Information filtering between teams creates misaligned expectations
Client Engagement Avoidance
Offshore teams avoid direct client-facing interactions
Lack of confidence leads to information distortion through proxies
"Operate in shadows" mindset — ownership not demonstrated to client
Misalignment with Client Intent
Resistance to client processes and compliance requirements
Frequent questioning of directives → execution friction
Business urgency and regulatory timelines not internalized
PwC | DevOps – Root Cause Classification | Confidential
Internal Use Only

## Slide 7
B · Process Issues: Execution Discipline & Ways of Working
Structural process failures that amplify delivery risk
01
Collaboration Overhead
Too many meetings, parallel chat groups, and communication threads with no governance on creation, closure, or action tracking. Cognitive overload reduces team throughput and obscures real blockers.
02
Fragmented Handoffs
Multiple handoffs across teams and time zones with leads requiring excessive guidance. Low autonomy at the individual contributor level extends cycle times and diffuses accountability.
03
PR & Release Misclassification
Pull Request delays are routinely labeled as DevOps failures. Actual root causes — code readiness, review cycle gaps, and quality defects — remain unaddressed because diagnosis is wrong.
04
Parallel Workstream Overload
Too many simultaneous initiatives run against an environment and pipeline not designed for parallelism. The result: resource contention, instability, and a perception that DevOps is the bottleneck.
PwC | DevOps – Root Cause Classification | Confidential
Internal Use Only

## Slide 8
C · System & Structural Issues: Org Design, Architecture & Tooling
Environmental constraints that teams work around — not through
Governance gap
🏛
No Unified DevOps Leadership
No single DevOps lead spans the full XD ecosystem. Ownership is fragmented across projects — standardization and cross-team visibility are absent by design.
Structural mismatch
🔧
Environment Constraints
The number of available environments does not match demand for parallel releases and faster timelines. High delivery ambition is running against constrained infrastructure.
Platform-induced lag
⚙️
Legacy Tooling (Client Side)
Fragmented DevOps tooling, slow adoption of modern platforms (e.g., Prism), and extended cycle times (e.g., Gearset delays) create system-induced inefficiencies misattributed to teams.
Toxic incentives
🏢
Multi-Vendor Competitive Dynamics
Multiple vendors (K-Force, TCS, etc.) operate with incentive models that promote fault-finding over collaboration. This creates pressure to route blame toward PwC DevOps regardless of true origin.
PwC | DevOps – Root Cause Classification | Confidential
Internal Use Only

## Slide 9
D · Project & SOW Issues: Planning, Scope & Release Model Design
Misalignment baked in at the contract and planning layer
PROJECT IS OPERATING WITH
Large, Bundled PRs
Each PR contains weeks of accumulated work across multiple features. This is the natural output of how the offshore team is structured and how code is reviewed.
Consequence:
• High-risk deployments
• Long regression cycles
• Deployment windows that don't match client cadence
• Single PR failure blocks multiple features
≠
CLIENT EXPECTS
Continuous / Bi-Weekly Releases
FPL leadership expects frequent, incremental releases — smaller units of value delivered on a predictable cadence aligned to business milestones.
Root Cause:
The SOW was not structured to define or enforce a release model. No contractual mechanism links delivery cadence to release frequency, leaving a structural gap that generates ongoing tension.
PwC | DevOps – Root Cause Classification | Confidential
Internal Use Only